## javier - project boar
Javier - Project Board
📌 Week 1–2: Introduction & Lab Setup
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Understand what a SOC is and what analysts do | Research SOC structure and analyst responsibilities,Identify essential technical and soft skills | Javier Napoles | Done | 2025-07-07 | 9402134841
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Research SOC structure and analyst responsibilities | Javier Napoles | Done |  | 9405562689
| Identify essential technical and soft skills | Javier Napoles | Done |  | 9405566677
Build the virtual lab (virtual machines, networking) | Installed UTM as the virtualization platform,Defined tech stack: Windows 10 (Victim), Parrot OS (Attacker), Ubuntu Server (SIEM Host),Created a shared project folder for documentation and screenshots,Create a network diagram,Configure internal or bridged networking between VMs | Javier Napoles | Working on it | 2025-07-14 | 9402134863
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Installed UTM as the virtualization platform |  | Done |  | 9557329070
| Defined tech stack: Windows 10 (Victim), Parrot OS (Attacker), Ubuntu Server (SIEM Host) |  | Done |  | 9557342372
| Created a shared project folder for documentation and screenshots |  | Done |  | 9557344183
| Create a network diagram | Javier Napoles | Working on it |  | 9405589651
| Configure internal or bridged networking between VMs | Javier Napoles | Working on it |  | 9405605490
Set up: | Windows 10 VM (Victim),Parrot OS VM (Attacker),Ubuntu Server (SIEM host) | Javier Napoles | Working on it | 2025-07-17 | 9405643923
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Windows 10 VM (Victim) | Javier Napoles |  |  | 9405653589
| Parrot OS VM (Attacker) | Javier Napoles |  |  | 9405655899
| Ubuntu Server (SIEM host) | Javier Napoles |  |  | 9405656712
📄 Deliverables | Documented environment setup,Network diagram,Screenshots of functional VMs | Javier Napoles | Working on it | 2025-07-17 | 9402134878
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Documented environment setup | Javier Napoles |  |  | 9405560972
| Network diagram | Javier Napoles |  |  | 9405599021
| Screenshots of functional VMs | Javier Napoles |  |  | 9405599899
2025-07-07 to 2025-07-17
📌 Week 3–4: Micro-Segmentation & Simulated Attacks
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Goals: Test attacks and begin proactive defense via segmentation |  | Javier Napoles |  | 2025-07-21 | 9405750050
✅ Tasks |  | Javier Napoles |  |  | 9402134908
Run simulated attacks | Port scans (nmap),Failed login attempts | Javier Napoles |  | 2025-07-23 | 9402134889
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Port scans (nmap) | Javier Napoles |  |  | 9405686890
| Failed login attempts | Javier Napoles |  |  | 9405686940
Implement micro-segmentation | Linux firewalls (iptables, ufw),Windows Defender Firewall | Javier Napoles |  | 2025-07-24 | 9405764733
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Linux firewalls (iptables, ufw) | Javier Napoles |  |  | 9405773513
| Windows Defender Firewall | Javier Napoles |  |  | 9405773577
Block lateral traffic between VMs |  | Javier Napoles |  | 2025-07-29 | 9405816569
Attempt to bypass segmentation (ping, netcat, etc.) |  | Javier Napoles |  | 2025-08-05 | 9405819617
📄 Deliverables | Firewall rule documentation,Segmentation policy table,Evidence (logs or screenshots) of blocked connections | Javier Napoles |  | 2025-08-14 | 9405824073
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Firewall rule documentation | Javier Napoles |  |  | 9405828902
| Segmentation policy table | Javier Napoles |  |  | 9405828945
| Evidence (logs or screenshots) of blocked connections | Javier Napoles |  |  | 9405829036
2025-07-21 to 2025-08-14
📁 Month 2: SIEM Setup & Alert Triage (Tier 1–2 Focus)
Name | Subitems | Person | Status | Date | Item ID (auto generated)
📌 Week 5–6: SIEM Setup & Log Ingestion | Goals: Set up a SIEM to collect and analyze logs | Javier Napoles |  | 2025-08-19 | 9405849971
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Goals: Set up a SIEM to collect and analyze logs | Javier Napoles |  |  | 9405852609
✅ Tasks: |  | Javier Napoles |  | 2025-08-20 | 9405856913
Choose and install SIEM (Wazuh, ELK, or Splunk Free) |  | Javier Napoles |  | 2025-08-20 | 9405858537
Install agents: | Winlogbeat (Windows),Filebeat/Auditd (Linux) | Javier Napoles |  | 2025-08-21 | 9405861069
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Winlogbeat (Windows) | Javier Napoles |  |  | 9405862195
| Filebeat/Auditd (Linux) | Javier Napoles |  |  | 9405862207
Forward logs to SIEM | Windows Event Logs,Linux Syslogs | Javier Napoles |  | 2025-08-21 | 9405864452
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Windows Event Logs | Javier Napoles |  |  | 9405865706
| Linux Syslogs | Javier Napoles |  |  | 9405865722
Verify log flow |  | Javier Napoles |  | 2025-08-26 | 9405868728
📄 Deliverables: | SIEM installed and running,Dashboards/screenshots of logs,Documentation of log sources | Javier Napoles |  | 2025-08-28 | 9405869706
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| SIEM installed and running | Javier Napoles |  |  | 9405870686
| Dashboards/screenshots of logs | Javier Napoles |  |  | 9405870714
| Documentation of log sources | Javier Napoles |  |  | 9405870742
2025-08-19 to 2025-08-28
📌 Week 7–8: Alert Rules & Playbooks
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Goals: Create detection rules and practice incident triage |  | Javier Napoles |  | 2025-09-02 | 9405880401
✅ Tasks |  | Javier Napoles |  | 2025-09-03 | 9405884616
Create rules | Failed logins,New user accounts,Suspicious file behavior | Javier Napoles |  | 2025-07-08 | 9405885374
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Failed logins | Javier Napoles |  |  | 9405890526
| New user accounts | Javier Napoles |  |  | 9405890552
| Suspicious file behavior | Javier Napoles |  |  | 9405890585
Simulate alerts with tools (Hydra, scripts, etc.) |  | Javier Napoles |  | 2025-09-09 | 9405898635
Analyze alerts (real vs. false positive) |  | Javier Napoles |  | 2025-09-11 | 9405899371
Write Tier 1 response playbooks | Account lockout,Suspicious process,Unusual file access | Javier Napoles |  | 2025-09-15 | 9405900185
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Account lockout |  |  |  | 9405900951
| Suspicious process |  |  |  | 9405900979
| Unusual file access |  |  |  | 9405900990
📄 Deliverables: | Detection rule exports,Alert screenshots,Playbooks (Notion subpages or PDF) | Javier Napoles |  | 2025-09-18 | 9405904123
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Detection rule exports | Javier Napoles |  |  | 9405905825
| Alert screenshots | Javier Napoles |  |  | 9405905843
| Playbooks (Notion subpages or PDF) | Javier Napoles |  |  | 9405905870
2025-07-08 to 2025-09-18
🔻 📁 Month 3: Threat Intel, Hunting & Final Report (Tier 2–3 Focus)
Name | Subitems | Person | Status | Date | Item ID (auto generated)
📌 Week 9–10: Threat Hunting & IOC Enrichment | Goals: Search logs for real-world threat indicators | Javier Napoles |  | 2025-09-22 | 9405911682
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Goals: Search logs for real-world threat indicators | Javier Napoles |  | 2025-09-23 | 9405912616
✅ Tasks | Use threat intel sources (OTX, AbuseIPDB, MISP),Search for IOCs (IPs, hashes, domains) in logs,Document threat hunting steps | Javier Napoles |  | 2025-09-23 | 9405921261
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Use threat intel sources (OTX, AbuseIPDB, MISP) | Javier Napoles |  | 2025-09-23 | 9405922989
| Search for IOCs (IPs, hashes, domains) in logs | Javier Napoles |  | 2025-09-24 | 9405923597
| Document threat hunting steps | Javier Napoles |  | 2025-09-25 | 9405923616
📄 Deliverables | IOC report with screenshots,Hunting checklist/process notes | Javier Napoles |  | 2025-10-02 | 9405925863
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| IOC report with screenshots | Javier Napoles |  | 2025-10-01 | 9405928042
| Hunting checklist/process notes | Javier Napoles |  | 2025-10-01 | 9405928059
2025-09-22 to 2025-10-02
📌 Week 11–12: Vulnerability Scanning & Final Report
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Goals: Assess vulnerabilities and summarize the entire lab experience |  | Javier Napoles |  | 2025-10-06 | 9405932692
✅ Tasks |  | Javier Napoles |  | 2025-10-07 | 9405936874
Scan VMs using: | Nmap,OpenVAS (optiona | Javier Napoles |  | 2025-10-08 | 9405941171
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Nmap | Javier Napoles |  |  | 9405942498
| OpenVAS (optiona | Javier Napoles |  |  | 9405944026
Prioritize vulnerabilities |  | Javier Napoles |  | 2025-10-15 | 9405945208
Recommend mitigations (patching, configs, firewall tweaks) |  | Javier Napoles |  | 2025-10-20 | 9405945818
Write final report |  | Javier Napoles |  | 2025-10-21 | 9405946310
📄 Final Deliverables: |  | Javier Napoles |  | 2025-10-23 | 9405947235
Final report including: | Lab setup,Micro-segmentation policy,Alert rules and screenshots,IOC findings,Vulnerability scan results,Optional: Presentation deck | Javier Napoles |  | 2025-10-23 | 9405956892
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Lab setup | Javier Napoles |  |  | 9405958015
| Micro-segmentation policy | Javier Napoles |  |  | 9405958049
| Alert rules and screenshots | Javier Napoles |  |  | 9405958082
| IOC findings | Javier Napoles |  |  | 9405958120
| Vulnerability scan results | Javier Napoles |  |  | 9405958165
| Optional: Presentation deck | Javier Napoles |  |  | 9405962656
2025-10-06 to 2025-10-23
Software needed
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Virtualization & VM Management | VirtualBox | Javier Napoles |  |  | 9427126361
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| VirtualBox |  |  |  | 9427127009
Operating Systems (VM ISOs) | Windows 10 ISO,Kali Linux,Ubuntu Server | Javier Napoles |  |  | 9427128820
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Windows 10 ISO |  |  |  | 9427129116
| Kali Linux |  |  |  | 9427129272
| Ubuntu Server |  |  |  | 9427129533
SIEM Platforms | Wazuh,ELK Stack (ElasticSearch, Logstash, Kibana),Splunk Free | Javier Napoles |  |  | 9427138600
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Wazuh |  |  |  | 9427138796
| ELK Stack (ElasticSearch, Logstash, Kibana) |  |  |  | 9427140416
| Splunk Free |  |  |  | 9427144010
Log Forwarders & Monitoring Agents | Winlogbeat,Filebeat,Auditd | Javier Napoles |  |  | 9427147051
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Winlogbeat |  |  |  | 9427147441
| Filebeat |  |  |  | 9427149857
| Auditd |  |  |  | 9427151922
Attack Simulation Tools | Nmap,Hydra (THC-Hydra),Metasploit Framework | Javier Napoles |  |  | 9427152996
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Nmap |  |  |  | 9427153142
| Hydra (THC-Hydra) |  |  |  | 9427154661
| Metasploit Framework |  |  |  | 9427156331
Firewall & Segmentation Tools | iptables,ufw (Uncomplicated Firewall),Windows Defender Firewall | Javier Napoles |  |  | 9427159812
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| iptables |  |  |  | 9427160160
| ufw (Uncomplicated Firewall) |  |  |  | 9427161002
| Windows Defender Firewall |  |  |  | 9427161806
Threat Intelligence & IOC Enrichment | AlienVault OTX,AbuseIPDB,MISP,CyberChef,VirusTotal | Javier Napoles |  |  | 9427163801
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| AlienVault OTX |  |  |  | 9427164096
| AbuseIPDB |  |  |  | 9427165441
| MISP |  |  |  | 9427166277
| CyberChef |  |  |  | 9427167171
| VirusTotal |  |  |  | 9427169596
Vulnerability Scanning Tools | OpenVAS / Greenbone,Nmap + NSE Scripts | Javier Napoles |  |  | 9427170652
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| OpenVAS / Greenbone |  |  |  | 9427170809
| Nmap + NSE Scripts |  |  |  | 9427171963
Documentation & Diagram Tools | draw.io (diagrams.net),Notion | Javier Napoles |  |  | 9427173645
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| draw.io (diagrams.net) |  |  |  | 9427173877
| Notion |  |  |  | 9427174541

## javier - project boar-updates
Javier - Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9405858537 | Choose and install SIEM (Wazuh, ELK, or Splunk Free) | Update |  | Javier Napoles | 18/June/2025 10:18:47 PM | https://documentation.wazuh.com/current/installation-guide/wazuh-agent/wazuh-agent-package-macos.htm... | 0 |  | 4219404733