## javier - project boar
Javier - Project Board
Phase 1 (week 1 to 4)
Name | Subitems | Person | Status | Timeline - Start | Timeline - End | Verify | Item ID (auto generated)
Start Cyberthreats & Vulnerabilities 1: complete 1st & 2nd rubric items | Install & configure VMs (Windows, Kali, Ubuntu); setup internal/bridged networking | Javier Napoles | Done | 2025-07-01 | 2025-07-07 |  | 9402134841
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Install & configure VMs (Windows, Kali, Ubuntu); setup internal/bridged networking | Javier Napoles | Done | 2025-07-08 | 2025-07-14 |  |  | 9405562689
Continue Cyberthreats & Vulnerabilities 1: finish 3rd–5th rubric items | Test VM communication; perform asset discovery and basic network map,Show asset discovery map & course progress on 2nd rubric | Javier Napoles | Working on it | 2025-07-08 | 2025-07-14 |  | 9563293969
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Test VM communication; perform asset discovery and basic network map | Javier Napoles | Working on it | 2025-07-08 | 2025-07-14 |  |  | 9563320209
| Show asset discovery map & course progress on 2nd rubric | [6 empty] | 9607303443
Start Cybersecurity Basics 1: complete 1st–3rd rubric items | Run basic attack simulations (Nmap, Hydra); check log capture | Javier Napoles | Working on it | 2025-07-15 | 2025-07-21 |  | 9402134863
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Run basic attack simulations (Nmap, Hydra); check log capture | Javier Napoles | Working on it | 2025-07-15 | 2025-07-21 |  |  | 9557329070
Finish Cybersecurity Basics 1: complete remaining rubric items & review both courses | Document lab setup + scans; if time, explore phishing template with SET | Javier Napoles | Working on it | 2025-07-21 | 2025-07-28 |  | 9405643923
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Document lab setup + scans; if time, explore phishing template with SET | Javier Napoles | Working on it |  |  |  |  | 9405653589
|  |  |  | 2025-07-01 | 2025-07-28 | 0/4
Phase 2 (week 5 to 8)
Name | Subitems | Person | Status | Timeline - Start | Timeline - End | Verify | Item ID (auto generated)
Start 2 new courses (Course A & B); skim syllabus and identify overlap with SOC tasks | Install & configure SIEM (Wazuh/ELK/Splunk); setup log forwarding,Report SIEM install progress + share course tracking sheet | Javier Napoles |  | 2025-08-04 | 2025-08-07 |  | 9405750050
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Install & configure SIEM (Wazuh/ELK/Splunk); setup log forwarding | [6 empty] | 9603815422
| Report SIEM install progress + share course tracking sheet | [6 empty] | 9603820439
Continue new courses; complete major rubric items for Course A | Create and test SIEM detection rules (failed logins, suspicious files) | Javier Napoles |  | 2025-08-07 | 2025-08-11 |  | 9402134908
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Create and test SIEM detection rules (failed logins, suspicious files) | Javier Napoles | [5 empty] | 9603902447
Work on Course B rubric items; explore how to integrate into SOC lab | Implement micro-segmentation rules (iptables/UFW/Windows Firewall) | Javier Napoles |  | 2025-08-12 | 2025-08-14 |  | 9607103442
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Implement micro-segmentation rules (iptables/UFW/Windows Firewall) | Javier Napoles | [5 empty] | 9607105685
Perform alert triage and test firewall bypass attempts | Review alert triage success + reflect on time balance between project/courses | Javier Napoles |  | 2025-08-18 | 2025-08-28 |  | 9607196902
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Review alert triage success + reflect on time balance between project/courses | [6 empty] | 9607205324
Wrap up both courses; submit/prepare deliverables if needed | Review alert triage success + reflect on time balance between project/courses | Javier Napoles |  | 2025-08-25 | 2025-08-28 |  | 9607181232
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Review alert triage success + reflect on time balance between project/courses | [6 empty] | 9607217547
|  |  |  | 2025-08-04 | 2025-08-28 | 0/5
Phase 3 (week 9 to 12)
Name | Subitems | Person | Status | Timeline - Start | Timeline - End | Verify | Item ID (auto generated)
Start Courses C & D; check for project-relevant concepts | Show IOC documentation + course startup notes,Perform IOC analysis from OTX/VirusTotal/MISP + log search | Javier Napoles |  | 2025-09-01 | 2025-09-04 |  | 9405849971
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Show IOC documentation + course startup notes | Javier Napoles | [5 empty] | 9405852609
| Perform IOC analysis from OTX/VirusTotal/MISP + log search | [6 empty] | 9607234414
Focus on Course C rubric; apply useful tools/ideas to lab (if applicable) | Present APT mapping progress + Course C rubric review,Map real APT campaign to MITRE ATT&CK & visualize mapping | Javier Napoles |  | 2025-09-08 | 2025-09-11 |  | 9405856913
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Present APT mapping progress + Course C rubric review | [6 empty] | 9607238185
| Map real APT campaign to MITRE ATT&CK & visualize mapping | [6 empty] | 9607239292
Continue Course D; prepare presentations/deliverables | Demo scan findings + discuss Course D progress,Conduct vulnerability scans (Nmap/OpenVAS); prioritize findings | Javier Napoles |  | 2025-09-22 | 2025-09-25 |  | 9607265073
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Demo scan findings + discuss Course D progress | [6 empty] | 9607266740
| Conduct vulnerability scans (Nmap/OpenVAS); prioritize findings | [6 empty] | 9607267892
Wrap up courses; do final review and submission | Submit final project report; reflect on 12-week journey,Write final report with screenshots, network diagram, and reflection | Javier Napoles |  | 2025-09-22 | 2025-09-26 |  | 9607269571
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify | Item ID (auto generated)
| Submit final project report; reflect on 12-week journey | [6 empty] | 9607270822
| Write final report with screenshots, network diagram, and reflection | [6 empty] | 9607273470
|  |  |  | 2025-09-01 | 2025-09-26 | 0/4

## javier - project boar-updates
Javier - Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9402134841 | Start Cyberthreats & Vulnerabilities 1: complete 1st & 2nd rubric items | Update |  | Abhinav Piratla | 16/July/2025 10:59:15 AM | You’ve marked this task as “Done,” but the first and second rubric items from Cyber Threats and Vulnerabilities 1 are not yet complete—please revisit and finish those before closing this task. Also, we’ve already finalized a new project plan, but I don’t see it updated on the board yet. Please upload or reflect the new plan as soon as possible. Let me know if you need help with either item. | 0 |  | 4323224203