## Sheet1
Week | Main Objective | Tasks (Security Monitoring 1) | Tasks (SOC Lab) | Project Integration
Week 5 | Consolidate the working environment for both projects. | Install and verify Wazuh + agents (Windows and Linux). Confirm log collection from 2 sources. Document monitoring architecture. | Configure network and basic micro-segmentation between VMs. Document SOC architecture and key tools. | Shared log sources and architecture. Wazuh as detection core for SOC Lab.
Week 6 | Create detection rules and apply logical segmentation. | Create 3 alert rules (auth, file, network). Test alerts with practical examples. Include screenshot evidence. | Document 3 detection scenarios in the SOC Lab. Refine micro-segmentation policies by asset type. Intentionally simulate alerts. | Same detection scenarios used across both. Shared evidence fuels rules and analysis.
Week 7 | Apply incident response methodology based on collected logs. | Analyze correlated logs. Build detection timeline. Classify severity and evaluate false positives. | Apply incident response steps based on protocol. Document escalation steps and decision points. Use realistic templates. | Wazuh timeline feeds SOC incident analysis. SOC protocols based on real detected events.
Week 8 | Present and professionally document both projects. | Create dashboards in Kibana/Wazuh. Generate security report with events and recommendations. Tune thresholds and visualizations. | Document alert flows and shift transitions. Publish everything on GitHub Pages with diagrams and screenshots. Prepare final presentation. | Monitoring visuals complement SOC reporting. Final delivery as joint semester project.