## javier - project boar
Javier - Project Board
Phase 2 (week 5 to 8) Semester 4
Name | Subitems | Person | Status | Timeline - Start | Timeline - End | Verify
Start : Security Operations Center 1: complete 1st & 2nd rubric items |  | Javier Napoles | Working on it | 2025-08-05 | 2025-08-07
Consolidate the working environment | TASKS (Security Monitoring 1),Install and verify Wazuh + agents (Windows and Linux).,Confirm log collection from 2 sources.,Document monitoring architecture.,TASKS (SOC Lab),Configure network and basic micro-segmentation between VMs.,Document SOC architecture and key tools. | Javier Napoles | Working on it | 2025-08-11 | 2025-08-15
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
TASKS (Security Monitoring 1)
| Install and verify Wazuh + agents (Windows and Linux). | Javier Napoles | Working on it | 2025-08-05 | 2025-08-06
| Confirm log collection from 2 sources. | Javier Napoles |  | 2025-08-06 | 2025-08-06
| Document monitoring architecture. | Javier Napoles
TASKS (SOC Lab)
| Configure network and basic micro-segmentation between VMs. | Javier Napoles
| Document SOC architecture and key tools. | Javier Napoles
Create detection rules and apply logical segmentation. | TASKS (Security Monitoring 1),Create 3 alert rules (auth, file, network).,Test alerts with practical examples.,Include screenshot evidence.,TASKS (SOC Lab),Document 3 detection scenarios in the SOC Lab.,Refine micro-segmentation policies by asset type.,Intentionally simulate alerts. | Javier Napoles |  | 2025-08-11 | 2025-08-14
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
| TASKS (Security Monitoring 1) | Javier Napoles
| Create 3 alert rules (auth, file, network). | Javier Napoles
| Test alerts with practical examples. | Javier Napoles
| Include screenshot evidence. | Javier Napoles
| TASKS (SOC Lab) | Javier Napoles
| Document 3 detection scenarios in the SOC Lab. | Javier Napoles
| Refine micro-segmentation policies by asset type. | Javier Napoles
| Intentionally simulate alerts. | Javier Napoles
Security Operations Center 1: Continue 3rd–4th rubric items |  | Javier Napoles |  | 2025-08-13 | 2025-08-18
Apply incident response methodology based on collected logs. | TASKS (Security Monitoring 1),Analyze correlated logs.,Build detection timeline.,Classify severity and evaluate false positives.,TASKS (SOC Lab),Apply incident response steps based on protocol.,Document escalation steps and decision points.,Use realistic templates. | Javier Napoles |  | 2025-08-18 | 2025-08-21
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
| TASKS (Security Monitoring 1) | Javier Napoles
| Analyze correlated logs. | Javier Napoles
| Build detection timeline. | Javier Napoles
| Classify severity and evaluate false positives. | Javier Napoles
| TASKS (SOC Lab) | Javier Napoles
| Apply incident response steps based on protocol. | Javier Napoles
| Document escalation steps and decision points. | Javier Napoles
| Use realistic templates. | Javier Napoles
Start : Security Monitoring 1: complete 1st & 2nd rubric items | Implement micro-segmentation rules (iptables/UFW/Windows Firewall) | Javier Napoles |  | 2025-08-12 | 2025-08-14
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
| Implement micro-segmentation rules (iptables/UFW/Windows Firewall) | Javier Napoles
Perform alert triage and test firewall bypass attempts | Review alert triage success + reflect on time balance between project/courses | Javier Napoles |  | 2025-08-18 | 2025-08-28
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
Review alert triage success + reflect on time balance between project/courses
Continue Security Monitoring 1: finish 3rd–4th rubric items |  | Javier Napoles |  | 2025-08-25 | 2025-08-28
Wrap up both courses; submit/prepare deliverables | Tasks (Security Monitoring 1),Create dashboards in Kibana/Wazuh.,Generate security report with events and recommendations.,Tune thresholds and visualizations.,Tasks (SOC Lab),Document alert flows and shift transitions.,Publish everything on GitHub Pages with diagrams and screenshots.,Prepare final presentation. | Javier Napoles |  | 2025-08-18 | 2025-08-28
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
Tasks (Security Monitoring 1)
Create dashboards in Kibana/Wazuh.
Generate security report with events and recommendations.
Tune thresholds and visualizations.
Tasks (SOC Lab)
Document alert flows and shift transitions.
Publish everything on GitHub Pages with diagrams and screenshots.
Prepare final presentation.
PROJECT INTEGRATION | WEEK 1,Shared log sources and architecture.,Wazuh as detection core for SOC Lab.,WEEK 2,Same detection scenarios used across both.,Shared evidence fuels rules and analysis.,WEEK 3,Wazuh timeline feeds SOC incident analysis.,SOC protocols based on real detected events.,WEEK 4,Monitoring visuals complement SOC reporting.,Final delivery as joint semester project. | Javier Napoles
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End | Date | Verify
| WEEK 1 | Javier Napoles
| Shared log sources and architecture. | Javier Napoles
| Wazuh as detection core for SOC Lab. | Javier Napoles
| WEEK 2 | Javier Napoles
| Same detection scenarios used across both. | Javier Napoles
| Shared evidence fuels rules and analysis. | Javier Napoles
| WEEK 3 | Javier Napoles
| Wazuh timeline feeds SOC incident analysis. | Javier Napoles
| SOC protocols based on real detected events. | Javier Napoles
| WEEK 4 | Javier Napoles
| Monitoring visuals complement SOC reporting. | Javier Napoles
| Final delivery as joint semester project. | Javier Napoles
|  |  |  | 2025-08-05 | 2025-08-28 | 0/10